## Week Mar26-Apr1
AI 1st SEO — Weekly Tasks (March 26 - April 1, 2026)
Dev | Category | Task | Status
Dev 1 — Deepthi (AI/ML)
Dev 1 | New | Begin building GEO Scanner Agent — orchestrator skeleton that coordinates scanner agents and returns structured results | To Do
Dev 1 | Cleanup | Wire GEO probe results to RDS — call POST /api/data/geo-probes and POST /api/data/ai-visibility from GEO engine | To Do
Dev 1 | Cleanup | Continue improving scanner output for non-technical users (Gurbachan feedback) | To Do
Dev 1 | Cleanup | Build comprehensive parameter reference list for AI visibility scanning | To Do
Dev 1 | Zoom | Add URL/link to new GEO page in admin dashboard, send to Gurbachan for review | To Do
Dev 1 | Zoom | Document and diagram SEO and content analysis workflows (process + value-add steps) | To Do
Dev 1 | Zoom | Deploy microproject to Linux server using OpenShell/NVIDIA open shell layer | To Do
Dev 1 | Zoom | Share deployment instructions with team | To Do
Dev 2 — Samarveer (Content & NLP)
Dev 2 | New | Build content scoring engine — expand compute_readability_score, compute_seo_score, compute_aeo_score to full 13+13 checks per DEV2-CHANGES.md | To Do
Dev 2 | Cleanup | Add get_content_briefs() and get_content_brief_by_id() to db.py — /api/content-briefs returns 500 without them | To Do
Dev 2 | Cleanup | Fix merge conflicts from this week's deploys | To Do
Dev 2 | Cleanup | Ensure Ollama fallback chain works end-to-end (Nova Lite → Ollama sageaios → Ollama databi → raw SERP) | To Do
Dev 2 | Zoom | Fix content brief generation and AI recommendations | To Do
Dev 2 | Zoom | Deploy microproject to Linux server | To Do
Dev 2 | Zoom | Share deployment instructions with team | To Do
Dev 3 — Troy (Data & Infrastructure)
Dev 3 | New | Build api_request_log middleware for tracking API usage — feeds admin dashboard analytics and future billing | Done
Dev 3 | Cleanup | Fully terminate EC2 and delete all associated resources (Elastic IPs, security groups, snapshots) | Done
Dev 3 | Cleanup | Coordinate with Amira on admin dashboard API if she needs changes | Done
Dev 3 | Zoom | Verify all EC2-related resources fully deleted (IPs, databases, sub-services) — Gurbachan stressed this | Done
Dev 3 | Zoom | Compile and send AI notes + task updates to team via WhatsApp | Done
Dev 3 | Zoom | Deploy microproject to Linux server | Done
Dev 3 | Zoom | Share deployment instructions with team | Done
Dev 3 | Zoom | Note: Main website updates (About Us, Privacy, Contact) = Amira's responsibility. Troy provides backend support if needed. | Done
Dev 4 — Tabasum (Integrations)
Dev 4 | New | Build social media content generation pipeline — use SEO info document as input for AI-generated posts via LLM fallback chain | Done
Dev 4 | Cleanup | Complete social post scheduler CRUD — data API at /api/data/social-posts is ready | Done
Dev 4 | Cleanup | Follow up with Gurbachan on Facebook/LinkedIn business account linking | In progress
Dev 4 | Cleanup | Test auth with direct Gmail address (not @ai1stseo.com forwarded) | Done
Dev 4 | Zoom | Implement Facebook and LinkedIn scheduling per Gurbachan's instructions | Done
Dev 4 | Zoom | Collect and store SEO info (Google, AEO, GEO) into document for AI content generation | Done
Dev 4 | Zoom | Test and potentially integrate PostIZ for social media scheduling on AWS | To Do
Dev 4 | Zoom | Email Paul and Gurbachan re: DynamoDB permission issues for Lambda execution role | Done
Dev 4 | Zoom | Troubleshoot forgot password email functionality | Done
Dev 4 | Zoom | Deploy microproject to Linux server | Done
Dev 4 | Zoom | Share deployment instructions with team | To Do
Dev 5 — Amira (Frontend & UX)
Dev 5 | New | Build admin dashboard UI using Troy's API endpoints — see AMIRA_ADMIN_HANDOFF.md and admin.html reference | Done
Dev 5 | Cleanup | Separate user dashboard from admin dashboard (ongoing from Mar 24) | Done
Dev 5 | Cleanup | Continue React + Vite migration | Done
Dev 5 | Cleanup | Coordinate with Samarveer on S3 deploys to avoid overwrites | Done
Dev 5 | Zoom | Move non-essential resources/diagrams/buttons from main website to admin dashboard | Done
Dev 5 | Zoom | Update main website: professional, advertising-friendly (About Us, Privacy Policy, Contact, developer info) | Done
Dev 5 | Zoom | Add free analysis section with PDF report feature (for marketing) | Done
Dev 5 | Zoom | Deploy microproject to Linux server | Done
Dev 5 | Zoom | Share deployment instructions with team | Done

## Week Apr1-Apr8
AI 1st SEO — Weekly Tasks (April 1 - April 8, 2026)
Dev | Category | Task | Status
Dev 1 — Deepthi (AI/ML)
Dev 1 | New | Conduct R&D on Agent Core functionality (from guide Phase 1 — orchestrator + scanner agents) | Done
Dev 1 | New | Review AI Business Directory document from Gurbachan and begin database setup on his server | done
Dev 1 | Cleanup | Continue Month 1 Research deliverables (8 API endpoints + UI — in progress) | done
Dev 1 | Cleanup | Ensure GEO scanner agent works end-to-end on her own Lambda (ai1stseo-geo-engine) | done
Dev 1 | Zoom | Work with Amira on overlapping SEO audit work and AI Business Directory project | done
Dev 1 | Zoom | Show progress on AI Business Directory understanding/setup by next meeting | done
Dev 1 | Zoom | Test Nova Lite for multi-modal content creation (images, videos) and report capabilities | done
Dev 2 — Samarveer (Content & NLP)
Dev 2 | New | Migrate content briefs persistence from RDS to DynamoDB per Gurbachan's directive | To Do
Dev 2 | New | Build content scoring engine with full 13+13 checks (carryover — still needed) | To Do
Dev 2 | Cleanup | Add get_content_briefs() and get_content_brief_by_id() to db.py (still missing from last week) | To Do
Dev 2 | Cleanup | Ensure Ollama fallback chain works end-to-end | To Do
Dev 2 | Cleanup | Fix any remaining merge conflicts | To Do
Dev 2 | Zoom | Extract necessary data from RDS before Troy shuts it down | To Do
Dev 2 | Zoom | Test Nova Lite for multi-modal content creation and report capabilities | To Do
Dev 3 — Troy (Data & Infrastructure)
Dev 3 | New | Begin working with OpenClaw on Gurbachan's server and report on integration progress | Done
Dev 3 | New | Plan DynamoDB migration strategy — map existing RDS tables to DynamoDB table designs per Gurbachan's directive | Done
Dev 3 | Cleanup | Verify EC2 fully terminated and no lingering resources (done — confirm with Paul) | Done
Dev 3 | Cleanup | Coordinate with team on RDS data extraction before shutdown | Done
Dev 3 | Zoom | Shut down Lightsail service to prevent further costs (ensure no data loss) | Done (Amira)
Dev 3 | Zoom | Shut down RDS/Postgres after confirming all team members have extracted necessary data | Done
Dev 3 | Zoom | Update and share current week's tasks in Excel spreadsheet via WhatsApp | Done
Dev 3 | Zoom | Note: Gurbachan is moving away from Postgres to individual DynamoDB tables per app. Plan migration accordingly. | Done
Dev 4 — Tabasum (Integrations)
Dev 4 | New | Build multi-modal content pipeline — test Nova Lite and Ollama for image/video generation | Done
Dev 4 | New | Explore Reddit integration for social media posting | done
Dev 4 | Cleanup | Continue resolving social media API connection issues (Facebook, Instagram, LinkedIn) | done
Dev 4 | Cleanup | Ensure marketing@ email can both send and receive replies for automation | done
Dev 4 | Cleanup | Complete social post scheduler CRUD (PR still unmerged — push to main) | done
Dev 4 | Zoom | Work with Samarveer (Summer) to resolve social media API connection issues | done
Dev 4 | Zoom | Test TikTok video posting and evaluate usefulness | To Do
Dev 4 | Zoom | Show progress/achievements on social media pipeline by next meeting | done
Dev 4 | Zoom | Deposit $5 into account for social media posting (per Gurbachan) | To Do
Dev 4 | Zoom | Test Nova Lite for multi-modal content creation (images, videos) | done
Dev 5 — Amira (Frontend & UX)
Dev 5 | New | Build email gate on PDF audit download — collect email before allowing download | Done
Dev 5 | New | Begin AI Business Directory project setup with Deepthi | Done
Dev 5 | Cleanup | Continue main website updates (About Us, Privacy Policy, Contact — contact.html is ready on repo) | Done
Dev 5 | Cleanup | Deploy contact.html to Amplify and link from homepage footer | Done
Dev 5 | Cleanup | Share admin dashboard passwords with team or help them create accounts | Done
Dev 5 | Zoom | Work with Deepthi on overlapping SEO audit work and AI Business Directory | Done
Dev 5 | Zoom | Review AI Business Directory document from Gurbachan | Done
Dev 5 | Zoom | Show progress on AI Business Directory understanding/setup by next meeting | Done
Dev 5 | Zoom | Forward AI notes to team for review | Done

## Week Apr8-Apr15
AI 1st SEO — Weekly Tasks (April 8 - April 15, 2026)
Dev | Category | Task | Status
Dev 1 — Deepthi (AI/ML)
Dev 1 | New | GEO Scanner: Add 5 new AI-readiness criteria to probe engine (WBS 1.3 — target 25 total GEO criteria) | done
Dev 1 | Cleanup | Investigate and document how business directory data is ingested into DynamoDB — prepare backend walkthrough for next meeting | done
Dev 1 | Cleanup | Ensure all GEO routes work on Lambda after DynamoDB migration (test geo-probe/models, aeo/analyze, chatbot/session) | done
Dev 1 | Zoom | Prepare demo of business directory backend + data ingestion process for next Tuesday meeting | done
Dev 1 | Zoom | Work with Amira on documenting the search/scraping pipeline for the AI Business Directory | done
Dev 1 | Zoom | Prepare to present backend details and search process at next meeting | done
Dev 2 — Samarveer (Content & NLP)
Dev 2 | New | Technical SEO Executor: Build auto-fix for sitemap.xml generation from scan results (WBS 2.1) | To Do
Dev 2 | Cleanup | Verify content-briefs and content-score endpoints work with DynamoDB (db_dynamo.py fallback) | Done
Dev 2 | Cleanup | Merge dev2-samar-merge branch to main if not already done | Done
Dev 2 | Zoom | Research two-way email send/receive solutions (SES vs ImprovMX vs iCloud) — report findings by Tuesday | Done
Dev 2 | Zoom | Provide iCloud email settings to Gurbachan for official business email setup | To Do
Dev 2 | Zoom | Send Gurbachan the automation hub / content generation demo link for review | Done
Dev 3 — Troy (Data & Infrastructure)
Dev 3 | New | Developer API: Document all 45+ API endpoints with request/response examples for team reference (WBS 6.2) | Done
Dev 3 | Cleanup | DynamoDB migration complete — monitor for any endpoint errors post-deploy | Done
Dev 3 | Cleanup | OpenClaw Gateway installed — wire up Phase 1 integration (report delivery via /hooks/agent) | In Progress
Dev 3 | Zoom | Send Gurbachan the OpenClaw research document for review | Done
Dev 3 | Zoom | Research NVIDIA OpenShell for security layer before OpenClaw — implement if feasible | Done
Dev 3 | Zoom | Prepare demo of DynamoDB migration + OpenClaw agent for next meeting | Done
Dev 4 — Tabasum (Integrations)
Dev 4 | New | GEO Executor: Implement FAQ schema auto-generation from scan results for social content (WBS 2.2) | To Do
Dev 4 | Cleanup | Merge dev4-tabasum-integrations branch to main (18 tests passing, CRUD complete — overdue) | To Do
Dev 4 | Cleanup | Resolve Facebook/Instagram account verification — use personal accounts per Gurbachan | Blocked
Dev 4 | Zoom | Set up official business accounts using personal accounts (not "business accounts") per Gurbachan | To Do
Dev 4 | Zoom | Work with Samarveer on email solution for social media account verification | To Do
Dev 4 | Zoom | Prepare demo of social scheduler + publishing pipeline for next meeting | To Do
Dev 5 — Amira (Frontend & UX)
Dev 5 | New | Basic Dashboard: Add before/after scan comparison view to audit results page (WBS 2.3) | Done
Dev 5 | Cleanup | Wire PDF email gate to POST /api/collect-email endpoint (now live on Lambda with DynamoDB) | Done
Dev 5 | Cleanup | Fix admin dashboard role check — DynamoDB auth is deployed, test admin access with amira.robleh@gmail.com | Done
Dev 5 | Zoom | Investigate and document business directory data ingestion with Deepthi — prepare for Tuesday demo | Done
Dev 5 | Zoom | Continue AI Business Directory frontend pages (category, compare, listing) | Done
Dev 5 | Zoom | Set up proper business email infrastructure with SES (send + receive) per Gurbachan | Done

## Week Apr15-Apr22
AI 1st SEO — Weekly Tasks (April 15 - April 22, 2026)
Dev | Category | Task | Status
Dev 1 — Deepthi (AI/ML)
Dev 1 | New | GEO Scanner: Expand AI-readiness criteria to 25 total and validate against live sites (WBS 1.3 continued) | To Do
Dev 1 | Cleanup | Provide estimate of records being added to directory database daily — present at next meeting | To Do
Dev 1 | Cleanup | Continue data scraping pipeline for Ottawa business records — ensure scraper runs continuously | In Progress
Dev 1 | Zoom | Research Amazon H100/H200 GPU accelerators — evaluate pricing and identify useful tasks from your workload | To Do
Dev 1 | Zoom | Collaborate with Amira, Tabasum, Samarveer on accelerator usage plan and recommendations for Gurbachan | To Do
Dev 1 | Zoom | Update shared Excel spreadsheet with task status; if blocked, add a note with the reason | To Do
Dev 2 — Samarveer (Content & NLP)
Dev 2 | New | Content scoring engine: Build AEO/GEO/SEO benchmark templates for service and manufacturing business types (WBS 4.1 — content criteria) | To Do
Dev 2 | New | Develop 3-4 perfect AEO/GEO/SEO templates for different business types (service, manufacturing, etc.) — per Gurbachan | To Do
Dev 2 | Cleanup | Determine how many possible template types are needed and document the scoring benchmarks (100% target) | To Do
Dev 2 | Cleanup | Ensure keyword clustering tool is stable on main after the app.py overwrite fix | Done
Dev 2 | Zoom | Research Amazon H100/H200 GPU accelerators — evaluate how they could improve keyword analysis and NLP work | To Do
Dev 2 | Zoom | Update shared Excel spreadsheet with task status; if blocked, add a note with the reason | To Do
Dev 3 — Troy (Data & Infrastructure)
Dev 3 | New | Developer API: Add rate limiting dashboard and usage analytics per API key (WBS 6.2 continued) | Done
Dev 3 | Cleanup | Add "investor" contact option/link at the bottom of the homepage for potential investors | Done
Dev 3 | Cleanup | Send final email to Gurbachan (CC Paul) re: OpenClaw/OpenShell Podman UDP socket permission issue | Done
Dev 3 | Cleanup | OpenShell sandbox — blocked on LXC seccomp restriction, waiting on Gurbachan | Blocked | Waiting on reply from Paul/Gurbachan with permissions
Dev 3 | Zoom | Research Amazon H100/H200 accelerator pricing and develop a usage plan for the team’s tiered job system | Done
Dev 3 | Zoom | Update shared Excel spreadsheet with task status; if blocked, add a note with the reason | Done
Dev 4 — Tabasum (Integrations)
Dev 4 | New | Social media API integration: Connect Buffer/Postiz publishers to live platform accounts and test end-to-end posting (WBS 3.4 — platform adapter) | To Do | Doing in steps based on the plan Mr Gurbachan sent me.
Dev 4 | Cleanup | Modify website email capture prompt — emphasize "free analysis" instead of "starter kit", list AEO/GEO before SEO | Done
Dev 4 | Cleanup | Send Paul email requesting SES SMTP permissions and additional credentials for marketing email | Done
Dev 4 | Zoom | Research Amazon H100/H200 GPU accelerators — evaluate pricing and identify useful tasks from your workload | Done
Dev 4 | Zoom | Collaborate with Deepthi, Amira, Samarveer on accelerator usage plan and recommendations for Gurbachan | Done
Dev 4 | Zoom | Update shared Excel spreadsheet with task status; if blocked, add a note with the reason | Done
Dev 5 — Amira (Frontend & UX)
Dev 5 | New | Basic Dashboard: Add score trend chart showing historical audit scores over time (WBS 2.3 continued) | Done
Dev 5 | Cleanup | Update before/after scan comparison tool — display highest changes at the top per Gurbachan | Done
Dev 5 | Cleanup | Wire Documents tab to live API endpoints (backend is deployed and matching your schema) | Done
Dev 5 | Cleanup | Wire PDF email gate to POST /api/collect-email endpoint (live on Lambda) | Done
Dev 5 | Zoom | Research Amazon H100/H200 GPU accelerators — evaluate pricing and identify useful tasks from your workload | Done
Dev 5 | Zoom | Update shared Excel spreadsheet with task status; if blocked, add a note with the reason | Done

## Week Apr22-Apr29
AI 1st SEO — Weekly Tasks (April 22 - April 29, 2026)
Dev | Category | Task | Status
Dev 1 — Deepthi (AI/ML)
Dev 1 | New | GEO Scanner: Implement off-page SEO signal detection for backlink and domain authority analysis (WBS 4.3) | To Do
Dev 1 | Cleanup | Add benchmark brands and real multi-brand data flows to GEO Score Tracker and keyword performance register | To Do
Dev 1 | Cleanup | Ensure directory page scraper runs continuously every 6 hours — monitor for crashes, extend timing per Gurbachan | In Progress
Dev 1 | Zoom | Research and implement tools for continuous daily content creation with time-stamped freshness (with Amira) | To Do
Dev 1 | Zoom | Conduct H100/H200 GPU experiments (4-5 hrs) — evaluate speed/quality for keyword analysis, present findings (with Amira) | To Do
Dev 1 | Zoom | Prepare all tools and features for Invest Ottawa demo by third week of May | To Do
Dev 2 — Samarveer (Content & NLP)
Dev 2 | New | Content Optimizer: Build LLM-powered content rewrite suggestions from audit results (WBS 5.1) | To Do
Dev 2 | Cleanup | Integrate template benchmark engine with Amira’s historical analysis / score tracking features | To Do
Dev 2 | Cleanup | Investigate where "AI First SEO" is mentioned or ranked in Claude, Gemini, and other AI platforms | To Do
Dev 2 | Zoom | Explore multi-agent AI system where different agents assess and update website content for changing AI models | To Do
Dev 2 | Zoom | Share competitor website examples with team for UI/UX inspiration | To Do
Dev 2 | Zoom | Prepare template benchmarks and content tools for Invest Ottawa demo by third week of May | To Do
Dev 3 — Troy (Data & Infrastructure)
Dev 3 | New | Webhook Integrations: Add Slack and email notification delivery for scan events (WBS 6.3) | To Do
Dev 3 | Cleanup | Wire OpenClaw agent to automated data collection pipeline per Gurbachan’s directive | To Do
Dev 3 | Cleanup | OpenShell sandbox — blocked on LXC seccomp fix from Gurbachan | Blocked
Dev 3 | Zoom | Implement content freshness automation — scheduled updates with timestamps for AI ranking maintenance | To Do
Dev 3 | Zoom | Ensure all backend infrastructure is demo-ready for Invest Ottawa by third week of May | To Do
Dev 3 | Zoom | Prepare demo of document repository + investor form + DynamoDB migration for Tuesday | To Do
Dev 4 — Tabasum (Integrations)
Dev 4 | New | Social media API integration: Connect live platform accounts for end-to-end posting (WBS 3.4 continued) | To Do
Dev 4 | Cleanup | Monitor website traffic and implement visitor tracking via cookies — report visitor numbers | To Do
Dev 4 | Cleanup | Continue creating engaging social media images/videos — use Pexel for images, Synthesia for lip-sync videos | To Do
Dev 4 | Zoom | Approach Algonquin College to explore partnership/advertising collaboration and offer free SEO services | To Do
Dev 4 | Zoom | Create more creative templates with clear text, animated/lady-led content for better engagement | To Do
Dev 4 | Zoom | Prepare social media pipeline and visitor tracking for Invest Ottawa demo by third week of May | To Do
Dev 5 — Amira (Frontend & UX)
Dev 5 | New | Multi-Site Dashboard: Begin agency view with bulk operations for multiple sites (WBS 6.1) | To Do
Dev 5 | Cleanup | Continue developing main landing page — highly user-friendly, engaging, clear CTAs, email capture | To Do
Dev 5 | Cleanup | Share competitor website example with team for UI/UX inspiration | To Do
Dev 5 | Zoom | Collaborate with Cairo to optimize main page for user engagement and conversion — debate best email collection approach | To Do
Dev 5 | Zoom | Research and implement daily content creation tools with time-stamped freshness for AI rankings (with Deepthi) | To Do
Dev 5 | Zoom | Have front-end prototype application ready for Invest Ottawa demo by third week of May | To Do